## Jira Backlog
Layer C POC Jira Backlog
Planner-first POC backlog aligned to the Layer C architecture
Issue ID | Phase | Epic | Module | Type | Feature / Story | Acceptance Criteria | Dependency | Size | Owner | Build Days | Buffer Days | Total Days | Suggested Window
LC-001 | 0 | Baseline | Shared | HLD | Define Layer C boundary & Orchestrator handshake | HLD published; Planner/Supervisor/Orchestrator split is explicit; happy-path and failure-path flow agreed | None | S | Architecture | 2 | 1 | 3 | W1
LC-002 | 0 | Baseline | Shared | Schema | Define RequestEnvelope, ExecutionPlan, TaskNode, StateCheckpoint, SupervisorDecision, ReplanRequest | Versioned Pydantic models + JSON schemas checked into repo; schema tests passing | LC-001 | M | Engineering | 3 | 2 | 5 | W1-W2
LC-003 | 1 | Planner POC | Planner | LLD | Design Planner input/output, prompt templates, and validation rules | LLD approved; prompt files and plan validation rules documented | LC-002 | S | Engineering | 2 | 1 | 3 | W2
LC-004 | 1 | Planner POC | Planner | Build | Implement intent-to-DAG generator | Planner accepts an intent and emits a valid ExecutionPlan with unique nodes and dependencies | LC-003 | L | Engineering | 5 | 2 | 7 | W2-W3
LC-005 | 1 | Planner POC | Planner | Build | Implement plan validator and retry logic | Invalid DAGs are rejected; cycles, missing fields, or unsupported node types trigger retry/repair | LC-004 | M | Engineering | 3 | 1 | 4 | W3-W4
LC-006 | 1 | Planner POC | Planner | Build | Implement re-plan API / method | Planner accepts partial state + failure reason and returns a new plan version | LC-005 | M | Engineering | 3 | 1 | 4 | W4
LC-007 | 2 | Supervisor POC | Supervisor | LLD | Design state transitions and supervisor decision policy | Decision thresholds and payload schemas documented for continue/replan/escalate/stop | LC-006 | S | Engineering | 2 | 1 | 3 | W5
LC-008 | 2 | Supervisor POC | Supervisor | Build | Implement state reader and execution monitor | Supervisor can parse active/completed/failed tasks, budget, and error signals from StateCheckpoint | LC-007 | M | Engineering | 3 | 1 | 4 | W5
LC-009 | 2 | Supervisor POC | Supervisor | Build | Implement decision engine | Supervisor emits one valid SupervisorDecision based on configured thresholds | LC-008 | L | Engineering | 5 | 2 | 7 | W5-W6
LC-010 | 2 | Supervisor POC | Supervisor | Build | Implement conflict / escalation detector | Conflicts, repeated failures, or low-confidence conditions trigger replan or escalate path | LC-009 | M | Engineering | 3 | 1 | 4 | W6
LC-011 | 3 | Integration | Orchestrator | Build | Wire Planner and Supervisor to Orchestrator loop | End-to-end execution loop works; state updates after each task; supervisor consulted at checkpoints | LC-006, LC-010 | L | Engineering | 6 | 2 | 8 | W7-W8
LC-012 | 3 | Integration | Platform | Telemetry | Instrument end-to-end traces | Traces capture plan version, task transitions, supervisor decisions, and latency per step | LC-011 | M | Platform | 3 | 1 | 4 | W7-W8
LC-013 | 4 | Evaluation | Architecture | Hardening | Score decomposition and decision quality | Golden-set evaluation scripts report DAG quality, false escalation, and missed escalation metrics | LC-011, LC-012 | M | Architecture | 4 | 1 | 5 | W9
LC-014 | 5 | Readout | Architecture | Readout | Prepare POC readout, demo, and phase-2 recommendation | Demo, reflection summary, backlog recommendation, and realistic next-phase scope delivered | LC-013 | S | Architecture | 2 | 1 | 3 | W10

## Task Timeline
Layer C POC Task Timeline
Week-based plan with explicit build effort and buffer
Issue ID | Phase | Module | Task / Story | Owner | Total Days | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10
LC-001 | 0 | Shared | Define Layer C boundary & Orchestrator handshake | Architecture | 3 | bar: W1
LC-002 | 0 | Shared | Define RequestEnvelope, ExecutionPlan, TaskNode, StateCheckpoint, SupervisorDecision, ReplanRequest | Engineering | 5 | bar: W1 to W2
LC-003 | 1 | Planner | Design Planner input/output, prompt templates, and validation rules | Engineering | 3 | bar: W2
LC-004 | 1 | Planner | Implement intent-to-DAG generator | Engineering | 7 | bar: W2 to W3
LC-005 | 1 | Planner | Implement plan validator and retry logic | Engineering | 4 | bar: W3 to W4
LC-006 | 1 | Planner | Implement re-plan API / method | Engineering | 4 | bar: W4
LC-007 | 2 | Supervisor | Design state transitions and supervisor decision policy | Engineering | 3 | bar: W5
LC-008 | 2 | Supervisor | Implement state reader and execution monitor | Engineering | 4 | bar: W5
LC-009 | 2 | Supervisor | Implement decision engine | Engineering | 7 | bar: W5 to W6
LC-010 | 2 | Supervisor | Implement conflict / escalation detector | Engineering | 4 | bar: W6
LC-011 | 3 | Orchestrator | Wire Planner and Supervisor to Orchestrator loop | Engineering | 8 | bar: W7 to W8
LC-012 | 3 | Platform | Instrument end-to-end traces | Platform | 4 | bar: W7 to W8
LC-013 | 4 | Architecture | Score decomposition and decision quality | Architecture | 5 | bar: W9
LC-014 | 5 | Architecture | Prepare POC readout, demo, and phase-2 recommendation | Architecture | 3 | bar: W10

## Sizing & Assumptions
Sizing and Timeline Assumptions
Size | Typical effort | Planning use | Notes
S | 1–3 days | small but important deliverable | Often design, config, contract, or readout work
M | 3–5 days | normal feature chunk | May still need 1 day of buffer
L | 5–8 days | core module or integration chunk | Likely to cross more than one week once testing is included
Assumptions
• | Timeline assumes one lead + one engineer with light platform support.
• | Buffers are intentionally included to absorb prompt tuning, schema drift, integration instability, and demo prep.
• | Week windows are relative and should be mapped to calendar dates once kickoff is approved.
• | This workbook is sized for the POC only, not the full enterprise platform roadmap.